## Plan1
Sprint 1 |  | Sprint 2
Metrica | Valor | Metrica | Valor
Budget At Complete (BAC) | 2200 | Budget At Complete (BAC) | 2200
Actual Cost (AC) | 2000 | Actual Cost (AC) | 2500
PRSP | 12 | PRSP | 19
Expected Percent Complete (EPC) | 33.33% | Expected Percent Complete (EPC) | 66.67%
Actual Percent Complete (APC) | 100% | Actual Percent Complete (APC) | 84.21%
Planned Value (PV) | 733.3333 | Planned Value (PV) | 1466.6667
Earned Value (EV) | 2000 | Earned Value (EV) | 2105.2632
CPI | 1 | CPI | 0.84211
SPI | 2.7273 | SPI | 1.4354